## Gantt Chart
DISSERTATION GANTT CHART — Jahangeer Khan ¦ MSc Artificial Intelligence ¦ SHU ¦ Supervisor: Prof. Jing Wang
Detecting Concept Drift in Non-IID Federated Learning Environments
Task / Milestone | Category | W1 May 1-7 | W2 May 8-14 | W3 May 15-21 | W4 May 22-31 | W5 Jun 1-7 | W6 Jun 8-14 | W7 Jun 15-21 | W8 Jun 22-30 | W9 Jul 1-7 | W10 Jul 8-14 | W11 Jul 15-21 | W12 Jul 22-31 | W13 Aug 1-7 | W14 Aug 8-14 | W15 Aug 15-21 | W16 Aug 22-31 | Sep Submit
━━━ MONTH 1: MAY 2026 — Setup + Literature + Basic FL ━━━
Read FedAvg paper (McMahan 2017) | Literature | ■
Read Open Problems paper (Kairouz 2021) | Literature | ■
Read CDA-FedAvg paper (Casado 2022) | Literature | ■
Read FL Drift Survey (Mahdi 2025) | Literature | ■
Write literature review notes — gaps identified | Literature | ■ | ■
Install Python env + libraries (flwr, torch, etc.) | Setup | ■
Run Flower quickstart tutorial | Setup |  | ■
Basic FedAvg with 5 clients + CIFAR-10 | Coding |  | ■
Plot accuracy graph — 20 rounds | Coding |  | ■
⭐ DEADLINE: Submit Proposal to Alice — 12th May | Deadline |  | ■
Implement Dirichlet Non-IID split (alpha=0.1,0.5,1.0) | Coding |  |  | ■
Run FedAvg on Non-IID — record accuracy drop | Experiment |  |  | ■
Implement sudden + gradual concept drift at Round 30 | Coding |  |  |  | ■
Run FedAvg with drift — record accuracy drop | Experiment |  |  |  | ■
Start writing Chapter 1: Introduction | Writing |  |  |  | ■
━━━ MONTH 2: JUNE 2026 — Cosine Similarity + Detection ━━━
Add gradient history storage to each client | Coding |  |  |  |  | ■
Implement cosine similarity: current vs historical gradients | Coding |  |  |  |  | ■
Plot cosine similarity: Non-IID (stable) vs Drift (sudden drop) | Results |  |  |  |  | ■ | ■
Find threshold separating Non-IID from Drift | Experiment | [5 empty] | ■
Calculate precision, recall, F1 of drift detection | Results | [5 empty] | ■
Write Chapter 2: Literature Review | Writing | [5 empty] | ■ | ■
Implement adaptive weight reduction for drifting clients | Coding | [6 empty] | ■
Run FedAvg vs Your Method — compare accuracy | Experiment | [6 empty] | ■
Implement CDA-FedAvg as second baseline | Coding | [7 empty] | ■
Compare all 3 methods under 4 conditions | Experiment | [7 empty] | ■
Build comparison table: accuracy results | Results | [7 empty] | ■
Write Chapter 3: Methodology | Writing | [7 empty] | ■
━━━ MONTH 3: JULY 2026 — Multi-Domain + Writing ━━━
Download + preprocess UNSW-NB15 (IoT dataset) | Setup | [8 empty] | ■
Run cosine similarity method on IoT dataset | Experiment | [8 empty] | ■
Download + preprocess Credit Card Fraud dataset | Setup | [9 empty] | ■
Run cosine similarity method on Finance dataset | Experiment | [9 empty] | ■
Produce final comparison graphs — all 3 methods + 3 datasets | Results | [10 empty] | ■
Upload all code to GitHub repository | Setup | [10 empty] | ■
Write Chapter 4: Results and Analysis | Writing | [10 empty] | ■ | ■
Create stakeholder evaluation questionnaire | Evaluation | [11 empty] | ■
Get expert feedback from Jing Wang | Evaluation | [11 empty] | ■
Reach out to finance/IoT professionals for feedback | Evaluation | [11 empty] | ■
Write Chapter 5: Discussion + Conclusion | Writing | [11 empty] | ■
━━━ AUGUST 2026 — Final Writing + Submit ━━━
Finalise all dissertation chapters | Writing | [12 empty] | ■ | ■
Write Abstract, References, Appendices | Writing | [12 empty] | ■ | ■
Proofread + format full dissertation | Final | [14 empty] | ■
Get Jing to review final draft | Final | [14 empty] | ■
Check all APA references | Final | [14 empty] | ■
⭐ SUBMIT DISSERTATION! | Deadline | [15 empty] | ■
LEGEND: |  | Literature |  | Coding |  | Experiment |  | Results |  | Writing |  | Evaluation |  | Setup |  | Deadline |  | Final